## Did Well
Did Well
Point | Votes
Nothing did well | 1
Good present, good job during phase 1 | 1
Tough phase 1 was gone | 0
Research Think up of ideas Improve layout with feedback Present the presentation Communicate with lecturers Communicate with customer Present demos Gather hardware detail Gather the best library for AI Organize scrum Improve from feedback | 0

## Anything bad？
Anything bad？
Point | Votes
we didn’t apply the skill we learn from ASDP & ASMP | 2
Tunjing didn’t heard wenyu advice and draw the db schema | 1
self learning and research we do is not enough | 1
Zero knowledge on react native | 1
Slides, didn't include the requirements and too many words | 1
We didn’t clarify the requirements and distribute to MoSCoW as soon as possible | 1
hard to get together after the daliy meeting, sometimes the meeting is too late | 1
Did not make the UI user friendly enough | 0
some times we got less passion when we discussed something | 0
Can't get components at time due to some component out of stock | 0

## What did you learn
What did you learn?
Point | Votes
using Adobe xd | 3
Planning release is a huge problem | 2
I learn we will fail this module | 1
How Arduino works | 1
i learn react native is a good framework | 1
GIS, EPA infor | 1
Comparing story point is difficult | 1
planning sprint is a disaster | 1
building Mahara collections | 1
How to use YOLOv3 and it's advantages and disadvantages | 0

## Improvement in next two sprint
Improvement in next two sprints
Point | Votes
Work hard and Try hard to cover the stuff we didn’t cover in last phase | 1
user friendly UI ? | 0
React native | 0
Plaing sptints sub-tasks | 0
YOLOv3 | 0